## TrelloExport
Organization | Board | List | Card # | Title | Link | Description | Total Checklist items | Completed Checklist items | Checklists | NumberOfComments | Comments | Attachments | Votes | Spent | Estimate | Points Estimate | Points Consumed | Created | CreatedBy | LastActivity | Due | Done | DoneBy | DoneTime | Members | Labels | Due Complete | Start
| 4350 Scrum Board | Reference Items | 4 | ERD (Will need to be modified) | https://trello.com/c/u3gkoQG8 | This is my old ERD from my Advanced Web final project. It will need to be modified, as it contains entities related to .NET’s Identity feature. ‌ - DexUsers can serve as a User profile entity - More ContactInfo and RecordCollector sub-entities can be added later on to expand functionality of the app | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 10:25:20 AM | Quinn Daniels | 2/12/2026 10:52:40 AM | [6 empty] | FALSE
| 4350 Scrum Board | Canceled Items | 23 | Convert GitHub Repo files .NET 10 -> .NET 9.0 | https://trello.com/c/u9HTAMnu |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 11:37:05 AM | Quinn Daniels | 2/12/2026 11:40:13 AM | [6 empty] | FALSE
| 4350 Scrum Board | Backlog | 26 | Add Debugging - Logging Services and Utilities | https://trello.com/c/CsMp0fph |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/15/2026 2:04:33 PM | Quinn Daniels | 2/15/2026 2:11:03 PM | [6 empty] | FALSE
| 4350 Scrum Board | Backlog | 1 | CRRUD Features for Social Records | https://trello.com/c/e9An9bVR |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/10/2026 11:34:58 AM | Ronan | 2/10/2026 11:34:58 AM | [6 empty] | FALSE
| 4350 Scrum Board | Backlog | 2 | Event Tags Filtering for Social Records | https://trello.com/c/DCyIhC9S |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/10/2026 11:35:34 AM | Ronan | 2/10/2026 11:35:34 AM | [6 empty] | FALSE
| 4350 Scrum Board | Backlog | 3 | Dynamic Records with entirely non-required categories | https://trello.com/c/CQhUgoZx |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/10/2026 11:43:07 AM | Ronan | 2/10/2026 11:50:26 AM | [6 empty] | FALSE
| 4350 Scrum Board | Backlog | 7 | Create an Entry | https://trello.com/c/FRjGWDRs | Create a new entry. This is pretty basic. No way to read an entry if it’s never made. Definition of Done: - User can create an entry. - Could use basic fields, but most should be nullable in case that info wasn’t gained through the interaction. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 10:42:00 AM | Jacob Robidas | 2/12/2026 11:21:53 AM | [5 empty] | Must | FALSE
| 4350 Scrum Board | Backlog | 6 | ReadDetailed View | https://trello.com/c/yTUwvnLE | Read a specific entry. This is more like a ‘Details’ page. It has more info. Read All is like the overview of the PokeDex while Read is more like when you select a specific Pokemon. Definition of Done: - The user is able to select an entry and see more details about it. - Multiple pieces of data could be linked to a single entry and separated like the tabs in the PokeDex. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 10:40:03 AM | Jacob Robidas | 2/12/2026 11:21:54 AM | [5 empty] | Must | FALSE
| 4350 Scrum Board | Backlog | 5 | Read All Entries | https://trello.com/c/mavZY5A8 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 10:34:32 AM | Jacob Robidas | 2/12/2026 10:39:46 AM | [5 empty] | Must | FALSE
| 4350 Scrum Board | Backlog | 9 | Edit Entries | https://trello.com/c/ZvvvXYrg | Each entry should be able to be updated. New information could be gained and added to a created entry. Definition of Done: - The user can select an entry and update its contents. - This could be a seamless process of just adding data to the entry or a more step-by-step process of select an ‘Edit’ button, editing the entry, and then clicking a ‘Save’ button. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 10:46:24 AM | Jacob Robidas | 2/12/2026 11:21:57 AM | [5 empty] | Must | FALSE
| 4350 Scrum Board | Backlog | 13 | Delete Entry | https://trello.com/c/F95juRpr | Users should be able to delete entries. Definition of Done: - Entries can be deleted. - Have an ‘Are you sure?’ check before deletion. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 11:20:07 AM | Jacob Robidas | 2/12/2026 11:22:01 AM | [5 empty] | Must | FALSE
| 4350 Scrum Board | Backlog | 11 | Front-end Visuals | https://trello.com/c/zR404Qpi | This is a necessary task, but the exact finalized version will shift throughout development. Goal is to look like a PokeDex, but we’ll just have to see how exactly that is achieved. Definition of Done: - Appealing, easily viewable front-end. - Optional: Pixel art style entries - Optional: Cool little animations similar to Gen 4 PokeDex. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 11:09:08 AM | Jacob Robidas | 2/12/2026 11:22:03 AM | [5 empty] | Must | FALSE
| 4350 Scrum Board | Backlog | 8 | OrganizeMove Entries | https://trello.com/c/dxO5IsXq | The entries should be able to either be movable, so the position is different relative to each other, or be filterable. This will help users find the specific entry he/she wants. Definition of Done: - Entries are movable either through a drag and drop feature or just some button presses to define its position in the list. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 10:43:51 AM | Jacob Robidas | 2/12/2026 10:45:52 AM | [5 empty] | Should | FALSE
| 4350 Scrum Board | Backlog | 10 | Sort Entries | https://trello.com/c/9dEOQEZN | User should be able to sort/filter by criteria. Probably just implement a read feature that checks specific fields. Definition of Done: - User can sort/filter by a specified field. - Sorted fields are in alphabetical order. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 11:06:06 AM | Jacob Robidas | 2/12/2026 11:08:30 AM | [5 empty] | Should | FALSE
| 4350 Scrum Board | Backlog | 12 | Relationship Tracker | https://trello.com/c/v6efMR8k | Within each entry is a ‘Relationship’ tab. This tab will show relationships between various entries. For example: John is the brother of Henry. Definition of Done: - Relationships are links, so that within an entry, another can be easily navigated to using the link. - Links only exist when the other entry exists. Otherwise, notes about relationships are simple text info. If Henry doesn’t exist, then John just has some note that says his brother is Henry. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 11:13:20 AM | Jacob Robidas | 2/12/2026 11:19:35 AM | [5 empty] | Should | FALSE
| 4350 Scrum Board | Backlog | 27 | Research - Viability of Docker containerization for automated testing | https://trello.com/c/0sqQ9Jtn |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/15/2026 2:13:37 PM | Quinn Daniels | 2/15/2026 2:13:37 PM | [6 empty] | FALSE
| 4350 Scrum Board | Backlog | 24 | Begin scaffolding Entity Models | https://trello.com/c/8PoE4TGM |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 11:37:51 AM | Quinn Daniels | 2/12/2026 11:37:51 AM | [6 empty] | FALSE
| 4350 Scrum Board | To-do (Current Sprint) | 28 | Create a 'Create Dex User' Branch | https://trello.com/c/3VMgIN5h | Make a branch for one of the Create functions. This would be the place for creating a dex user. This is, probably, the most basic object and the one we will need the most. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/19/2026 10:49:52 AM | Jacob Robidas | 2/19/2026 10:51:26 AM |  |  |  |  | Jacob Robidas | Must | FALSE
| 4350 Scrum Board | In Progress | 20 | Environment Configuration - D | https://trello.com/c/nfd2yjmL | Configure team IDEs to work with new Visual Studio updates and Emulator software. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 11:33:13 AM |  | 2/12/2026 11:33:14 AM | [5 empty] | Must | FALSE
| 4350 Scrum Board | In Progress | 21 | Local SQLite Database Connection | https://trello.com/c/X9uRHGrb | Manage NuGet package installation. Install sqlite-net-pcl configure connection [https://learn.microsoft.com/en-us/training/modules/store-local-data/4-exercise-store-data-locally-with-sqlite](https://learn.microsoft.com/en-us/training/modules/store-local-data/4-exercise-store-data-locally-with-sqlite "smartCard-inline") ‌ [https://learn.microsoft.com/en-us/dotnet/maui/data-cloud/database-sqlite?view=net-maui-10.0](https://learn.microsoft.com/en-us/dotnet/maui/data-cloud/database-sqlite?view=net-maui-10.0 "smartCard-inline") | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 11:35:36 AM | Quinn Daniels | 2/12/2026 11:46:07 AM |  |  |  |  | Quinn Daniels |  | FALSE
| 4350 Scrum Board | Completed (Current Sprint) | 18 | Environment Configuration - J | https://trello.com/c/s7LODdG1 | Configure team IDEs to work with new Visual Studio updates and Emulator software. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 11:32:41 AM |  | 2/19/2026 10:45:24 AM |  |  |  |  | Jacob Robidas | Must | TRUE
| 4350 Scrum Board | Completed (Current Sprint) | 25 | Set up initial (concept) UI | https://trello.com/c/joI6EIQ3 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 11:40:48 AM | McKinney, Kaleb John | 2/19/2026 11:59:23 AM | 2/19/2026 12:00:00 PM |  |  |  | McKinney, Kaleb John | Must | TRUE | 2/10/2026 8:00:00 AM
| 4350 Scrum Board | Completed in Sprint 1 | 15 | GitHub repository init | https://trello.com/c/1GBgmNF3 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 11:31:23 AM | McKinney, Kaleb John | 2/12/2026 12:04:06 PM | 2/12/2026 11:31:00 AM |  |  |  | McKinney, Kaleb John | Urgent | TRUE | 2/10/2026 8:00:00 AM
| 4350 Scrum Board | Completed in Sprint 1 | 14 | Environment Configuration - R | https://trello.com/c/u34fPXmr | Configure team IDEs to work with new Visual Studio updates and Emulator software. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 11:30:23 AM | Jacob Robidas | 2/17/2026 12:12:54 PM |  |  |  |  | Ronan | Must | TRUE
| 4350 Scrum Board | Completed in Sprint 1 | 19 | Environment Configuration - K | https://trello.com/c/KT6T8AMU | Configure team IDEs to work with new Visual Studio updates and Emulator software. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 11:32:51 AM |  | 2/12/2026 12:04:07 PM |  |  |  |  | McKinney, Kaleb John | Must | TRUE
| 4350 Scrum Board | Completed in Sprint 1 | 17 | Environment Configuration - Q | https://trello.com/c/aLQCiMH2 | Configure team IDEs to work with new Visual Studio updates and Emulator software. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 11:32:30 AM |  | 2/12/2026 12:04:08 PM |  |  |  |  | Quinn Daniels | Must | TRUE
| 4350 Scrum Board | Completed in Sprint 1 | 22 | Set Up Trello Board | https://trello.com/c/4r7TIP42 | Create the initial draft of the Trello Board. This should include basic backlog components and swim lanes. Definition of Done: - Create the Trello Board - Add basic Backlog items - Add swim lanes for each stage of development | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 11:36:06 AM | Jacob Robidas | 2/12/2026 12:04:10 PM |  |  |  |  | Jacob Robidas | Must | TRUE

## Archived
Organization | Board | List | Card # | Title | Link | Description | Total Checklist items | Completed Checklist items | Checklists | NumberOfComments | Comments | Attachments | Votes | Spent | Estimate | Points Estimate | Points Consumed | Created | CreatedBy | LastActivity | Due | Done | DoneBy | DoneTime | Members | Labels | Due Complete | Start