## TrelloExport
Organization | Board | List | Card # | Title | Link | Description | Total Checklist items | Completed Checklist items | Checklists | NumberOfComments | Comments | Attachments | Votes | Spent | Estimate | Points Estimate | Points Consumed | Created | CreatedBy | LastActivity | Due | Done | DoneBy | DoneTime | Members | Labels | Due Complete | Start
| 4350 Scrum Board | Canceled Items | 23 | Convert GitHub Repo files .NET 10 -> .NET 9.0 | https://trello.com/c/u9HTAMnu |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 11:37:05 AM | Quinn Daniels | 2/12/2026 11:40:13 AM | [6 empty] | FALSE
| 4350 Scrum Board | Canceled Items | 27 | Research - Viability of Docker containerization for automated testing | https://trello.com/c/0sqQ9Jtn |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/15/2026 2:13:37 PM | Quinn Daniels | 2/26/2026 10:33:54 AM | [6 empty] | FALSE
| 4350 Scrum Board | Canceled Items | 47 | Debug View ReadAll with includes | https://trello.com/c/myn4cNp8 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/3/2026 12:53:15 PM | Quinn Daniels | 3/31/2026 10:26:58 AM |  |  |  |  | Quinn Daniels | Should | FALSE
| 4350 Scrum Board | Reference Items | 4 | ERD (Will need to be modified) | https://trello.com/c/u3gkoQG8 | This is my old ERD from my Advanced Web final project. It will need to be modified, as it contains entities related to .NET’s Identity feature. ‌ - DexUsers can serve as a User profile entity - More ContactInfo and RecordCollector sub-entities can be added later on to expand functionality of the app | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 10:25:20 AM | Quinn Daniels | 2/12/2026 10:52:40 AM | [6 empty] | FALSE
| 4350 Scrum Board | Reference Items | 29 | CSCI 2020 ERD (Use only as reference for field data types) | https://trello.com/c/06jp3Pft | An archaic form of what we are attempting. I’ve only included it because it may be useful as a jumping point when it comes to data-types for entity fields. Do not take as gospel | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/24/2026 10:55:37 AM | Quinn Daniels | 2/24/2026 10:58:17 AM | [6 empty] | FALSE
| 4350 Scrum Board | Reference Items | 70 | Person Page Example 1 | https://trello.com/c/6bXkEZPJ |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 11:27:22 AM | Ronan | 3/24/2026 11:27:47 AM | [6 empty] | FALSE
| 4350 Scrum Board | Documentation Backlog (GitHub) | 51 | Product vision | https://trello.com/c/9OHASKu1 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 10:57:34 AM | Quinn Daniels | 3/24/2026 10:57:34 AM | [6 empty] | FALSE
| 4350 Scrum Board | Documentation Backlog (GitHub) | 52 | Project goals; Release plan | https://trello.com/c/2l2qtLAB |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 10:57:47 AM | Quinn Daniels | 3/24/2026 10:57:47 AM | [6 empty] | FALSE
| 4350 Scrum Board | Documentation Backlog (GitHub) | 54 | Exported copy of the TrelloPlanner Board with backloag and individual sprint items clearly marked. | https://trello.com/c/WtiRooKu |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 10:58:16 AM | Quinn Daniels | 3/24/2026 10:58:16 AM | [6 empty] | FALSE
| 4350 Scrum Board | Documentation Backlog (GitHub) | 56 | Coding standards | https://trello.com/c/8sB0KVQ2 | - Case Style - Naming Conventions - Where does documentation go? | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 10:58:40 AM | Quinn Daniels | 3/24/2026 11:11:26 AM | [5 empty] | Must | FALSE
| 4350 Scrum Board | Documentation Backlog (GitHub) | 57 | Documentation standards | https://trello.com/c/o8vvbmC1 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 10:59:08 AM | Quinn Daniels | 3/24/2026 10:59:08 AM | [6 empty] | FALSE
| 4350 Scrum Board | Documentation Backlog (GitHub) | 58 | Development Environment (tech stack) | https://trello.com/c/3JOnDT4K |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 10:59:19 AM | Quinn Daniels | 3/24/2026 10:59:19 AM | [6 empty] | FALSE
| 4350 Scrum Board | Documentation Backlog (GitHub) | 59 | Deployment Environment | https://trello.com/c/8y41hUZv |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 10:59:26 AM | Quinn Daniels | 3/24/2026 10:59:26 AM | [6 empty] | FALSE
| 4350 Scrum Board | Documentation Backlog (GitHub) | 60 | Version Management | https://trello.com/c/1snEHXHb |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 10:59:32 AM | Quinn Daniels | 3/24/2026 10:59:32 AM | [6 empty] | FALSE
| 4350 Scrum Board | Documentation Backlog (GitHub) | 61 | Test plan, tests performed (and test types), and analysis reports | https://trello.com/c/FfElpxk2 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 10:59:52 AM | Quinn Daniels | 3/24/2026 10:59:52 AM | [6 empty] | FALSE
| 4350 Scrum Board | Documentation Backlog (GitHub) | 62 | Test automation, if any | https://trello.com/c/M4zAukRu |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 10:59:57 AM | Quinn Daniels | 3/24/2026 10:59:57 AM | [6 empty] | FALSE
| 4350 Scrum Board | Documentation Backlog (GitHub) | 63 | Change management; bug tracking process | https://trello.com/c/3RML1myl |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 11:00:08 AM | Quinn Daniels | 3/24/2026 11:00:08 AM | [6 empty] | FALSE
| 4350 Scrum Board | Documentation Backlog (GitHub) | 64 | definition of ready | https://trello.com/c/IX23dMLR |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 11:00:15 AM | Quinn Daniels | 3/24/2026 11:00:15 AM | [6 empty] | FALSE
| 4350 Scrum Board | Documentation Backlog (GitHub) | 65 | definition of done | https://trello.com/c/OS4mQg2s |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 11:00:20 AM | Quinn Daniels | 3/24/2026 11:00:20 AM | [6 empty] | FALSE
| 4350 Scrum Board | Documentation Backlog (GitHub) | 66 | architectural design | https://trello.com/c/bxIBRjBJ |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 11:00:26 AM | Quinn Daniels | 3/24/2026 11:00:26 AM | [6 empty] | FALSE
| 4350 Scrum Board | Documentation Backlog (GitHub) | 67 | detailed design | https://trello.com/c/Rn5MD3hD |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 11:00:33 AM | Quinn Daniels | 3/24/2026 11:00:33 AM | [6 empty] | FALSE
| 4350 Scrum Board | Documentation Backlog (GitHub) | 68 | UIUX Design | https://trello.com/c/74z7pIv5 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 11:00:38 AM | Quinn Daniels | 3/24/2026 11:00:38 AM | [6 empty] | FALSE
| 4350 Scrum Board | Documentation Backlog (GitHub) | 71 | README | https://trello.com/c/H6NC5luP |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 11:56:16 AM | Quinn Daniels | 3/24/2026 11:56:16 AM | [6 empty] | FALSE
| 4350 Scrum Board | Documentation Backlog (GitHub) | 78 | doc in GitHub - Sprint Report 8 | https://trello.com/c/bFAOEca8 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 11:58:44 AM | Quinn Daniels | 3/24/2026 12:01:01 PM | [6 empty] | FALSE
| 4350 Scrum Board | Documentation Backlog (GitHub) | 79 | doc in GitHub - Sprint Report 9 | https://trello.com/c/hF81KH5U |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 11:58:49 AM | Quinn Daniels | 3/24/2026 12:01:07 PM | [6 empty] | FALSE
| 4350 Scrum Board | Documentation Backlog (GitHub) | 80 | doc in GitHub - Sprint Report 10 | https://trello.com/c/sZ799T9j |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 11:59:03 AM | Quinn Daniels | 3/24/2026 12:01:13 PM | [6 empty] | FALSE
| 4350 Scrum Board | Documentation In Progress | 55 | Source code (perpetual) | https://trello.com/c/4v23kt9B |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 10:58:30 AM | Quinn Daniels | 3/24/2026 11:06:48 AM | [6 empty] | FALSE
| 4350 Scrum Board | Documentation In Progress | 72 | doc in GitHub - Sprint Report 1 | https://trello.com/c/DPfWX4ff |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 11:58:17 AM | Quinn Daniels | 4/2/2026 12:08:38 PM | [6 empty] | FALSE
| 4350 Scrum Board | Documentation In Progress | 73 | doc in GitHub - Sprint Report 2 | https://trello.com/c/j1vwVUWc |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 11:58:22 AM | Quinn Daniels | 4/2/2026 12:08:41 PM | [6 empty] | FALSE
| 4350 Scrum Board | Documentation In Progress | 74 | doc in GitHub - Sprint Report 4 | https://trello.com/c/rRZEaclD |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 11:58:27 AM | Quinn Daniels | 4/2/2026 12:08:43 PM | [6 empty] | FALSE
| 4350 Scrum Board | Documentation In Progress | 75 | doc in GitHub - Sprint Report 5 | https://trello.com/c/djch092D |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 11:58:31 AM | Quinn Daniels | 4/2/2026 12:08:45 PM | [6 empty] | FALSE
| 4350 Scrum Board | Documentation In Progress | 76 | doc in GitHub - Sprint Report 6 | https://trello.com/c/ZxyuCz4Y |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 11:58:35 AM | Quinn Daniels | 4/2/2026 12:08:48 PM | [6 empty] | FALSE
| 4350 Scrum Board | Documentation In Progress | 77 | doc in GitHub - Sprint Report 7 | https://trello.com/c/h4mZCEt8 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 11:58:39 AM | Quinn Daniels | 4/2/2026 12:08:50 PM | [6 empty] | FALSE
| 4350 Scrum Board | User Stories/Epics | 37 | As a User, I want to move a Person to Trash, in case I want to restore them | https://trello.com/c/ugcgrWEF |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/26/2026 11:16:24 AM | Quinn Daniels | 2/26/2026 11:27:03 AM | [5 empty] | Should | FALSE
| 4350 Scrum Board | User Stories/Epics | 38 | As a User, I want to erase Person(s) in Trash either manually, or automatically after a set amount of time | https://trello.com/c/TCm4qm8C |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/26/2026 11:19:17 AM | Quinn Daniels | 2/26/2026 11:27:15 AM | [5 empty] | Should | FALSE
| 4350 Scrum Board | Backlog | 26 | Add Debugging - Logging Services and Utilities | https://trello.com/c/CsMp0fph |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/15/2026 2:04:33 PM | Quinn Daniels | 2/15/2026 2:11:03 PM | [6 empty] | FALSE
| 4350 Scrum Board | Backlog | 33 | UI Page Mockup - Rooms | https://trello.com/c/K1PlX150 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/26/2026 10:38:52 AM | Quinn Daniels | 2/26/2026 1:40:52 PM | [6 empty] | FALSE
| 4350 Scrum Board | Backlog | 2 | Event Tags Filtering for Social Records | https://trello.com/c/DCyIhC9S |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/10/2026 11:35:34 AM | Ronan | 2/10/2026 11:35:34 AM | [6 empty] | FALSE
| 4350 Scrum Board | Backlog | 8 | OrganizeMove Entries | https://trello.com/c/dxO5IsXq | The entries should be able to either be movable, so the position is different relative to each other, or be filterable. This will help users find the specific entry he/she wants. Definition of Done: - Entries are movable either through a drag and drop feature or just some button presses to define its position in the list. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 10:43:51 AM | Jacob Robidas | 2/12/2026 10:45:52 AM | [5 empty] | Should | FALSE
| 4350 Scrum Board | Backlog | 32 | UI Page Mockup - Person | https://trello.com/c/jU09jNuW |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/26/2026 10:38:35 AM | Quinn Daniels | 4/2/2026 10:18:29 AM |  |  |  |  | Ronan |  | FALSE
| 4350 Scrum Board | To-do (Current Sprint) | 42 | Create an ERD. | https://trello.com/c/HreS8eqB | Create an ERD for the current iteration of the database. This will help us better understand the database. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/3/2026 10:27:16 AM | Jacob Robidas | 3/3/2026 10:28:56 AM |  |  |  |  | Jacob Robidas |  | FALSE
| 4350 Scrum Board | To-do (Current Sprint) | 11 | Front-end Visuals | https://trello.com/c/zR404Qpi | This is a necessary task, but the exact finalized version will shift throughout development. Goal is to look like a PokeDex, but we’ll just have to see how exactly that is achieved. Definition of Done: - Appealing, easily viewable front-end. - Optional: Pixel art style entries - Optional: Cool little animations similar to Gen 4 PokeDex. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 11:09:08 AM | Jacob Robidas | 4/2/2026 12:07:39 PM |  |  |  |  | Ronan | Must | FALSE
| 4350 Scrum Board | To-do (Current Sprint) | 12 | Relationship Tracker | https://trello.com/c/v6efMR8k | Within each entry is a ‘Relationship’ tab. This tab will show relationships between various entries. For example: John is the brother of Henry. Definition of Done: - Relationships are links, so that within an entry, another can be easily navigated to using the link. - Links only exist when the other entry exists. Otherwise, notes about relationships are simple text info. If Henry doesn’t exist, then John just has some note that says his brother is Henry. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 11:13:20 AM | Jacob Robidas | 4/2/2026 12:07:46 PM | [5 empty] | Should | FALSE
| 4350 Scrum Board | In Progress | 13 | Delete Entry | https://trello.com/c/F95juRpr | Users should be able to delete entries. Definition of Done: - Entries can be deleted. - Have an ‘Are you sure?’ check before deletion. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 11:20:07 AM | Jacob Robidas | 4/2/2026 12:07:07 PM | [5 empty] | Must | FALSE
| 4350 Scrum Board | Completed (Current Sprint) | 35 | As a User, I want to View a Person | https://trello.com/c/JS7gxkPQ |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/26/2026 11:11:53 AM | Quinn Daniels | 4/2/2026 12:06:01 PM | [5 empty] | Must | TRUE
| 4350 Scrum Board | Completed (Current Sprint) | 36 | As a User, I want to Edit a Person's Details | https://trello.com/c/gMRxBzbf |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/26/2026 11:14:30 AM | Quinn Daniels | 4/2/2026 12:06:05 PM | [5 empty] | Must | TRUE
| 4350 Scrum Board | Completed (Current Sprint) | 9 | Edit Entries | https://trello.com/c/ZvvvXYrg | Each entry should be able to be updated. New information could be gained and added to a created entry. Definition of Done: - The user can select an entry and update its contents. - This could be a seamless process of just adding data to the entry or a more step-by-step process of select an ‘Edit’ button, editing the entry, and then clicking a ‘Save’ button. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 10:46:24 AM | Jacob Robidas | 4/2/2026 12:07:02 PM | [5 empty] | Must | TRUE
| 4350 Scrum Board | Completed in Sprint 1 | 15 | GitHub repository init | https://trello.com/c/1GBgmNF3 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 11:31:23 AM | McKinney, Kaleb John | 2/12/2026 12:04:06 PM | 2/12/2026 11:31:00 AM |  |  |  | McKinney, Kaleb John | Urgent | TRUE | 2/10/2026 8:00:00 AM
| 4350 Scrum Board | Completed in Sprint 1 | 14 | Environment Configuration - R | https://trello.com/c/u34fPXmr | Configure team IDEs to work with new Visual Studio updates and Emulator software. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 11:30:23 AM | Jacob Robidas | 2/17/2026 12:12:54 PM |  |  |  |  | Ronan | Must | TRUE
| 4350 Scrum Board | Completed in Sprint 1 | 19 | Environment Configuration - K | https://trello.com/c/KT6T8AMU | Configure team IDEs to work with new Visual Studio updates and Emulator software. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 11:32:51 AM |  | 2/12/2026 12:04:07 PM |  |  |  |  | McKinney, Kaleb John | Must | TRUE
| 4350 Scrum Board | Completed in Sprint 1 | 17 | Environment Configuration - Q | https://trello.com/c/aLQCiMH2 | Configure team IDEs to work with new Visual Studio updates and Emulator software. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 11:32:30 AM |  | 2/12/2026 12:04:08 PM |  |  |  |  | Quinn Daniels | Must | TRUE
| 4350 Scrum Board | Completed in Sprint 1 | 22 | Set Up Trello Board | https://trello.com/c/4r7TIP42 | Create the initial draft of the Trello Board. This should include basic backlog components and swim lanes. Definition of Done: - Create the Trello Board - Add basic Backlog items - Add swim lanes for each stage of development | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 11:36:06 AM | Jacob Robidas | 2/12/2026 12:04:10 PM |  |  |  |  | Jacob Robidas | Must | TRUE
| 4350 Scrum Board | Completed in Sprint 2 | 18 | Environment Configuration - J | https://trello.com/c/s7LODdG1 | Configure team IDEs to work with new Visual Studio updates and Emulator software. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 11:32:41 AM |  | 2/24/2026 10:30:25 AM |  |  |  |  | Jacob Robidas | Must | TRUE
| 4350 Scrum Board | Completed in Sprint 2 | 25 | Set up initial (concept) UI | https://trello.com/c/joI6EIQ3 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 11:40:48 AM | McKinney, Kaleb John | 2/24/2026 10:30:29 AM | 2/19/2026 12:00:00 PM |  |  |  | McKinney, Kaleb John | Must | TRUE | 2/10/2026 8:00:00 AM
| 4350 Scrum Board | Completed in Sprint 2 | 21 | Local SQLite Database Connection | https://trello.com/c/X9uRHGrb | Manage NuGet package installation. Install sqlite-net-pcl configure connection [https://learn.microsoft.com/en-us/training/modules/store-local-data/4-exercise-store-data-locally-with-sqlite](https://learn.microsoft.com/en-us/training/modules/store-local-data/4-exercise-store-data-locally-with-sqlite "smartCard-inline") ‌ [https://learn.microsoft.com/en-us/dotnet/maui/data-cloud/database-sqlite?view=net-maui-10.0](https://learn.microsoft.com/en-us/dotnet/maui/data-cloud/database-sqlite?view=net-maui-10.0 "smartCard-inline") | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 11:35:36 AM | Quinn Daniels | 2/24/2026 10:53:57 AM |  |  |  |  | Quinn Daniels |  | TRUE
| 4350 Scrum Board | Completed in Sprint 2 | 20 | Environment Configuration - D | https://trello.com/c/nfd2yjmL | Configure team IDEs to work with new Visual Studio updates and Emulator software. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 11:33:13 AM |  | 2/26/2026 10:42:51 AM | [5 empty] | Must | TRUE
| 4350 Scrum Board | Completed in Sprint 3 | 31 | Add EF Core to project | https://trello.com/c/7H7DaCLD | Add Entity Framework Core for SQLite to project for database usage | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/24/2026 12:24:02 PM | McKinney, Kaleb John | 3/3/2026 10:15:50 AM | 2/25/2026 12:24:27 PM |  |  |  | McKinney, Kaleb John | Expedite | TRUE | 2/25/2026 8:00:00 AM
| 4350 Scrum Board | Completed in Sprint 3 | 30 | Sqlite-net-pcl --> ef-core ORM conversion | https://trello.com/c/DWNrgCjU | SQLite-net-pcl does not elegantly handle foreign keys. To handle this, we will need to adapt what we currently have to ef-core. Things to consider later on: [https://learn.microsoft.com/en-us/ef/core/providers/sqlite/limitations](https://learn.microsoft.com/en-us/ef/core/providers/sqlite/limitations "smartCard-inline") | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/24/2026 11:03:24 AM | Quinn Daniels | 3/3/2026 10:15:54 AM |  |  |  |  | McKinney, Kaleb John | Expedite,Must | TRUE
| 4350 Scrum Board | Completed in Sprint 3 | 24 | Begin scaffolding Entity Models | https://trello.com/c/8PoE4TGM | Add Entity Models for Entry, Room, Entry Blocks, etc., roughly following the ERD posted in the reference items | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 11:37:51 AM | Quinn Daniels | 3/3/2026 10:15:56 AM |  |  |  |  | McKinney, Kaleb John | Urgent | TRUE
| 4350 Scrum Board | Completed in Sprint 3 | 28 | Create a 'CRRUD Person' Branch | https://trello.com/c/3VMgIN5h | Make a branch for one of the Create functions. This would be the place for creating a dex user. This is, probably, the most basic object and the one we will need the most. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/19/2026 10:49:52 AM | Jacob Robidas | 3/3/2026 10:16:10 AM |  |  |  |  | Jacob Robidas | Must | FALSE
| 4350 Scrum Board | Completed in Sprint 3 | 40 | Design Elements - Icon | https://trello.com/c/vSilf0Gs |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/26/2026 11:55:55 AM | Quinn Daniels | 3/3/2026 10:24:48 AM |  |  |  |  | Ronan |  | TRUE
| 4350 Scrum Board | Completed in sprint 4 | 41 | Design Elements - Splash Image | https://trello.com/c/aHaZY6zo |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/26/2026 1:40:20 PM | Ronan | 3/10/2026 10:27:01 AM |  |  |  |  | Ronan |  | TRUE
| 4350 Scrum Board | Completed in sprint 4 | 44 | Add Debug Page | https://trello.com/c/lmTBIklG | expected half an hour, took about that | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/3/2026 11:56:24 AM | Ronan | 3/10/2026 10:27:01 AM |  |  |  |  | Ronan |  | TRUE
| 4350 Scrum Board | Completed in sprint 4 | 50 | UI Page Visuals - Home | https://trello.com/c/HTsWuGFw |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/5/2026 12:13:27 PM | Ronan | 3/10/2026 10:27:01 AM |  |  |  |  | Ronan |  | TRUE
| 4350 Scrum Board | Completed in Sprint 5 | 46 | Create Room Page | https://trello.com/c/56mfTOof |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/3/2026 12:08:21 PM | McKinney, Kaleb John | 3/24/2026 10:24:42 AM |  |  |  |  | Eloghosa Erhabor,McKinney, Kaleb John | Must | TRUE
| 4350 Scrum Board | Completed in Sprint 5 | 43 | Create Person Page | https://trello.com/c/Fdahg1ZR |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/3/2026 10:48:57 AM | McKinney, Kaleb John | 3/24/2026 10:24:42 AM |  |  |  |  | Jacob Robidas | Must,Urgent | TRUE
| 4350 Scrum Board | Completed in Sprint 5 | 49 | Create operation for Person object | https://trello.com/c/2tnrXBGS | Implement the Create operation for the Person object. Definition of Done: - Repository function created - ViewModel intermediary created - Fields and inputs on CreatePage made - New Person object is created on submission | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/5/2026 12:13:01 PM | Jacob Robidas | 3/24/2026 10:33:24 AM |  |  |  |  | Jacob Robidas | Must | FALSE
| 4350 Scrum Board | Completed in Sprint 5 | 34 | As a User, I want to Create a Person | https://trello.com/c/gSvbcLMe |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/26/2026 11:11:38 AM | Quinn Daniels | 3/24/2026 11:28:56 AM | [5 empty] | Must | TRUE
| 4350 Scrum Board | Completed in Sprint 5 | 7 | Create an Entry | https://trello.com/c/FRjGWDRs | Create a new entry. This is pretty basic. No way to read an entry if it’s never made. Definition of Done: - User can create an entry. - Could use basic fields, but most should be nullable in case that info wasn’t gained through the interaction. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 10:42:00 AM | Jacob Robidas | 3/24/2026 11:29:02 AM | [5 empty] | Must | TRUE
| 4350 Scrum Board | Completed in Sprint 5 | 5 | Read All Entries | https://trello.com/c/mavZY5A8 | Create a Read All function. The user can see all of his/her entries likely from the start/home page. Definition of Done: - User can easily see all entries created. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 10:34:32 AM | Jacob Robidas | 3/24/2026 10:24:42 AM |  |  |  |  | Jacob Robidas | Must | TRUE
| 4350 Scrum Board | Completed in Sprint 5 | 45 | Seed Database in Debug Environments | https://trello.com/c/eXcUAZp9 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/3/2026 12:00:26 PM | Quinn Daniels | 3/24/2026 10:32:40 AM |  |  |  |  | Quinn Daniels | Should | TRUE
| 4350 Scrum Board | Completed in Sprint 5 | 48 | Set up database seeding for testing purposes | https://trello.com/c/Rehr3dAQ | Add a database seeding script for debug environments so we can test with the database | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/5/2026 10:38:05 AM | McKinney, Kaleb John | 3/24/2026 10:33:12 AM |  |  |  |  | Quinn Daniels | Should | TRUE
| 4350 Scrum Board | Completed in Sprint 6 | 69 | Documentation Scaffolding | https://trello.com/c/c2t2adgf | Adding documentation items as a backlog Preparing github folders | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 11:01:48 AM | Quinn Daniels | 4/2/2026 12:06:50 PM |  |  |  |  | Quinn Daniels | Should | TRUE
| 4350 Scrum Board | Completed in Sprint 6 | 82 | doc in GitHub - Sprint Report 3 | https://trello.com/c/FwjLtvSn |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 12:01:30 PM | Quinn Daniels | 4/2/2026 10:17:55 AM |  |  |  |  | Quinn Daniels |  | TRUE
| 4350 Scrum Board | Completed in Sprint 6 | 83 | doc in GitHub - Project Proposal Presentation | https://trello.com/c/655haFJV |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 12:02:12 PM | Quinn Daniels | 4/2/2026 10:17:57 AM |  |  |  |  | Quinn Daniels |  | TRUE
| 4350 Scrum Board | Completed in Sprint 6 | 39 | As a user, I want to change my preferences to adjust the visuals of the app | https://trello.com/c/0OgvwJUH |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/26/2026 11:26:02 AM | Quinn Daniels | 4/2/2026 10:18:00 AM |  |  |  |  | Ronan | Could | TRUE
| 4350 Scrum Board | Completed in Sprint 6 | 10 | Sort Entries | https://trello.com/c/9dEOQEZN | User should be able to sort/filter by criteria. Probably just implement a read feature that checks specific fields. Definition of Done: - User can sort/filter by a specified field. - Sorted fields are in alphabetical order. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 11:06:06 AM | Jacob Robidas | 4/2/2026 10:18:02 AM |  |  |  |  | Ronan | Should | TRUE
| 4350 Scrum Board | Completed in Sprint 6 | 6 | ReadDetailed View | https://trello.com/c/yTUwvnLE | Read a specific entry. This is more like a ‘Details’ page. It has more info. Read All is like the overview of the PokeDex while Read is more like when you select a specific Pokemon. Definition of Done: - The user is able to select an entry and see more details about it. - Multiple pieces of data could be linked to a single entry and separated like the tabs in the PokeDex. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/12/2026 10:40:03 AM | Jacob Robidas | 4/2/2026 10:18:15 AM |  |  |  |  | McKinney, Kaleb John | Must | TRUE | 3/24/2026 8:00:00 AM
| 4350 Scrum Board | Completed in Sprint 6 | 81 | Create Block Components | https://trello.com/c/KPIAXI7B | Create components for our blocks, one for each block type. These components will be used for displaying the DexEntry for each Person entry | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3/24/2026 12:00:05 PM | McKinney, Kaleb John | 4/2/2026 10:18:19 AM |  |  |  |  | McKinney, Kaleb John | Must | TRUE | 3/24/2026 8:00:39 AM
| 4350 Scrum Board | Completed in Sprint 6 | 3 | Dynamic Records with entirely non-required categories | https://trello.com/c/CQhUgoZx |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/10/2026 11:43:07 AM | Ronan | 4/2/2026 12:07:53 PM | [6 empty] | TRUE
| 4350 Scrum Board | Completed in Sprint 6 | 1 | CRRUD Features for Social Records | https://trello.com/c/e9An9bVR |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2/10/2026 11:34:58 AM | Ronan | 4/2/2026 12:09:00 PM | [6 empty] | TRUE

## Archived
Organization | Board | List | Card # | Title | Link | Description | Total Checklist items | Completed Checklist items | Checklists | NumberOfComments | Comments | Attachments | Votes | Spent | Estimate | Points Estimate | Points Consumed | Created | CreatedBy | LastActivity | Due | Done | DoneBy | DoneTime | Members | Labels | Due Complete | Start