## TrelloExport
Organization | Board | List | Card # | Title | Link | Description | Total Checklist items | Completed Checklist items | Checklists | NumberOfComments | Comments | Attachments | Votes | Spent | Estimate | Points Estimate | Points Consumed | Created | CreatedBy | LastActivity | Due | Done | DoneBy | DoneTime | Members | Labels | Due Complete | Start
| Scrum Board Test | How to use this Board | 34 | Card with DoR and DoD | https://trello.com/c/0jj4U04k |  | 0 | 0 | Definition of Ready (0 items): Definition of Done (0 items): | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 1/22/2026 11:08:20 AM |  | 2/12/2026 10:09:34 AM | [6 empty] | FALSE
| Scrum Board Test | Backlog / Cancelled Features | 6 | Instructor - Adding Students to Course | https://trello.com/c/4mKXHobj | - As an [Instructor], I want to [Add students to my course], so that [I can ensure that students are able to participate in activities] - Acceptance Criteria: Instructors have the ability to add students to courses | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10/6/2025 12:33:29 PM | Jacob Robidas | 11/24/2025 11:15:38 AM |  | 11/19/2025 10:57:00 AM | Eanes, Ronan | P43DT23H23M31S |  | Won't | FALSE
| Scrum Board Test | Backlog / Cancelled Features | 7 | Instructor - Removing Students from Course | https://trello.com/c/7XpGdCxi | - As an [Instructor], I want to [Remove students from my course], so that [I can remove students that are not actually in my class] - Acceptance Criteria: Instructors have the ability to remove students from courses | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10/8/2025 11:29:31 AM | Jacob Robidas | 11/24/2025 11:15:49 AM | [5 empty] | Won't | FALSE
| Scrum Board Test | Backlog / Cancelled Features | 23 | _Incorportating initializing functions | https://trello.com/c/v3ZGWHyl | Definition of done: - write 2-3 rows to each currently existing table - ideally: establish a new db on first run ‌ Estimate, overall: ~4 hours | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10/20/2025 12:19:12 PM | Quinn Daniels | 10/27/2025 12:17:00 PM | [5 empty] | Won't | FALSE
| Scrum Board Test | Backlog / Cancelled Features | 27 | _Attach SignalR services to Azure | https://trello.com/c/R37hxhib |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 11/5/2025 10:43:59 AM | Quinn Daniels | 11/19/2025 10:58:05 AM | [5 empty] | Won't | FALSE
| Scrum Board Test | Done / Completed in Sprint 5 | 8 | ETSU Rep - App Follows ETSU Design Guidelines | https://trello.com/c/qX9jwAJR | - As a [University Brand Manager], I want to [ensure that all ETSU affiliated applications/websites follow the university design guidelines], so that [the application/website is more easily linked to the university and to ensure that no offensive/inappropriate designs are produced]. - Acceptance Criteria: Meets the design guidelines of the university -> [https://www.etsu.edu/brand/design.php](https://www.etsu.edu/brand/design.php "smartCard-inline") | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10/8/2025 11:31:05 AM | Jacob Robidas | 11/24/2025 11:16:35 AM |  | 11/24/2025 11:15:53 AM | Eanes, Ronan | P47DT0H44M48S | Eanes, Ronan,Jacob Robidas,McKinney, Kaleb John | Must | TRUE
| Scrum Board Test | Done / Completed in Sprint 5 | 33 | _Messaging Group Chat functionality | https://trello.com/c/64kf7HLd |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 11/24/2025 11:16:22 AM | Eanes, Ronan | 11/24/2025 11:16:44 AM |  |  |  |  | Quinn Daniels |  | TRUE
| Scrum Board Test | Completed in Sprint 1 | 14 | _Brainstorming: Database Architecture | https://trello.com/c/bckVAiSh |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10/15/2025 1:12:36 PM | Quinn Daniels | 10/22/2025 12:15:38 PM |  |  |  |  | Jacob Robidas |  | TRUE
| Scrum Board Test | Completed in Sprint 1 | 12 | _Device Geolocation | https://trello.com/c/QeFNeZOo |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10/8/2025 12:02:02 PM | Quinn Daniels | 10/22/2025 12:15:15 PM |  | 10/22/2025 10:59:06 AM | McKinney, Kaleb John | P13DT22H57M3S | McKinney, Kaleb John |  | TRUE
| Scrum Board Test | Completed in Sprint 1 | 13 | _UserAccountScaffolding | https://trello.com/c/blALaIFN | Creating the scaffolding for User Accounts in the Blazor Web App Project Template | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10/8/2025 12:03:03 PM | Quinn Daniels | 10/22/2025 12:15:16 PM |  | 10/20/2025 10:39:52 AM | Jacob Robidas | P11DT22H36M49S | Jacob Robidas | Must | TRUE
| Scrum Board Test | Completed in Sprint 1 | 11 | _WebPages | https://trello.com/c/n2VlgGSm |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10/8/2025 11:46:54 AM | Quinn Daniels | 10/22/2025 12:15:36 PM |  | 10/20/2025 10:38:25 AM | Eanes, Ronan | P11DT22H51M31S | Eanes, Ronan,McKinney, Kaleb John |  | TRUE
| Scrum Board Test | Completed in Sprint 1 | 10 | _Establish GitHub Repo | https://trello.com/c/kdYmcM4I |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10/8/2025 11:46:23 AM | Quinn Daniels | 10/22/2025 12:15:37 PM |  | 10/8/2025 12:24:02 PM | McKinney, Kaleb John | P0DT0H37M38S | McKinney, Kaleb John |  | TRUE
| Scrum Board Test | Completed in Sprint 1 | 15 | _Prelim Blazor Template | https://trello.com/c/b3zq3lZc |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10/15/2025 1:13:22 PM | Quinn Daniels | 10/22/2025 12:15:40 PM |  |  |  |  | McKinney, Kaleb John |  | TRUE
| Scrum Board Test | Completed in Sprint 1 | 9 | _Preliminary Database | https://trello.com/c/Ojd1NccT | - Simple ERD (minimum) | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10/8/2025 11:33:22 AM | Quinn Daniels | 10/22/2025 12:15:41 PM |  | 10/17/2025 7:09:18 PM | Jacob Robidas | P9DT7H35M55S | Jacob Robidas |  | TRUE
| Scrum Board Test | Completed in Sprint 2 | 25 | _Set up SQLite | https://trello.com/c/lhnuB5tm | Set up the SQLite file so that we can begin testing. We can switch it out for a proper SQL server later, but we need something to begin testing and move on with the project. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10/22/2025 12:16:15 PM | Jacob Robidas | 10/27/2025 11:18:07 AM |  | 10/27/2025 10:38:08 AM | Jacob Robidas | P4DT22H21M52S | McKinney, Kaleb John |  | TRUE
| Scrum Board Test | Completed in Sprint 2 | 16 | _Create Dummy Data | https://trello.com/c/IxuchXCD | Create the dummy data for the database for testing purposes. Probably want 2 Courses, 2 Instructors, and 5 Students to test many-to-many relationships. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10/20/2025 10:39:06 AM | Jacob Robidas | 10/27/2025 11:18:08 AM |  | 10/27/2025 10:38:02 AM | Jacob Robidas | P6DT23H58M56S | Jacob Robidas | Should | TRUE
| Scrum Board Test | Completed in Sprint 2 | 19 | _Finish Timecard Class | https://trello.com/c/YNgZpSFJ | Timecard class is unfinished. Needs Location data. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10/20/2025 11:52:18 AM | Jacob Robidas | 10/27/2025 11:18:12 AM |  | 10/22/2025 12:15:56 PM | Jacob Robidas | P2DT0H23M38S | Jacob Robidas | Must | TRUE
| Scrum Board Test | Completed in Sprint 2 | 17 | _Fix Instructor Class | https://trello.com/c/Y00cNRcG | Need to include the UserId parameter with the ForeignKey for the ApplicationUser class. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10/20/2025 11:22:35 AM | Jacob Robidas | 10/27/2025 11:18:14 AM |  | 10/22/2025 12:15:54 PM | Jacob Robidas | P2DT0H53M18S | Jacob Robidas | Must | TRUE
| Scrum Board Test | Completed in Sprint 2 | 20 | _Create Message Class | https://trello.com/c/W3NJ9fpz | Create the Message class. Needs parameters such as Id, MessageBody, UserId | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10/20/2025 11:56:07 AM | Jacob Robidas | 10/27/2025 11:18:18 AM |  | 10/22/2025 12:15:53 PM | Jacob Robidas | P2DT0H19M45S | Jacob Robidas | Must | TRUE
| Scrum Board Test | Completed in Sprint 3 | 26 | _Login Updates Student Table | https://trello.com/c/0xZrr0dW | The Login page should update the Student table to allow for smoother operation. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10/27/2025 10:50:06 AM | Jacob Robidas | 11/5/2025 12:15:17 PM |  | 10/29/2025 11:08:49 AM | McKinney, Kaleb John | P2DT0H18M42S | McKinney, Kaleb John |  | TRUE
| Scrum Board Test | Completed in Sprint 3 | 2 | Student - Location logging (make entry) | https://trello.com/c/GHXess1U | - As a [Student], I want to [log my location] so that [the Instructor can verify that I stayed On-Prem during an On-Site visit] - Acceptance Criteria: A logging function exists within the application to track location and date data (timecard). | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10/6/2025 12:27:11 PM | Jacob Robidas | 11/5/2025 12:15:19 PM |  | 10/29/2025 11:47:59 AM | McKinney, Kaleb John | P22DT23H20M48S |  | Must | TRUE
| Scrum Board Test | Completed in Sprint 3 | 22 | _Test Login Functionality | https://trello.com/c/oxbWjuFu | The Login functionality needs to be tested. Need Dummy Data for it. Def of Done: - Login page built. - Tested with both Student and Instructor accounts. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10/20/2025 11:59:07 AM | Jacob Robidas | 11/5/2025 12:15:20 PM |  | 11/5/2025 11:06:48 AM | Jacob Robidas | P16DT0H7M40S |  | Must | TRUE
| Scrum Board Test | Completed in Sprint 3 | 28 | _Add Authorization to Site Pages | https://trello.com/c/dFJL0xER | Add authorization to the site to ensure that only users who are logged in can view pages other than the registration/login page. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 11/5/2025 11:07:06 AM | Jacob Robidas | 11/5/2025 12:15:22 PM |  |  |  |  | Eanes, Ronan | Should | TRUE
| Scrum Board Test | Completed in Sprint 3 | 30 | _Registration Overhaul | https://trello.com/c/EhvMnrmd | Overhaul the registration so that user’s data is added to the Student table. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 11/5/2025 11:10:55 AM | Jacob Robidas | 11/5/2025 12:15:24 PM |  | 11/5/2025 11:12:48 AM | Jacob Robidas | P0DT0H1M53S | McKinney, Kaleb John | Must | TRUE
| Scrum Board Test | Completed in Sprint 4 | 4 | Instructor - Message students | https://trello.com/c/VT6DzghW | - As an [instructor], I’ll need to be able to [quickly communicate with the students], even if we are not in the same place. o Acceptance criteria: chat feature allows the instructor to chat with students from within the app | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10/6/2025 12:30:13 PM | Quinn Daniels | 11/19/2025 11:17:00 AM |  | 11/19/2025 10:57:31 AM | Eanes, Ronan | P43DT23H27M18S |  | Should | TRUE
| Scrum Board Test | Completed in Sprint 4 | 31 | _Roles Based Funcionality | https://trello.com/c/K1gbNdXP | Assign certain functions, such as viewing all Students within a Course, to the classes based on the role they have. This is primarily for Instructors, but Students may have a case where it’s needed. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 11/5/2025 12:16:15 PM | Jacob Robidas | 11/19/2025 11:17:04 AM |  | 11/19/2025 10:55:38 AM | Jacob Robidas | P13DT22H39M23S | Jacob Robidas,McKinney, Kaleb John | Must | TRUE
| Scrum Board Test | Completed in Sprint 4 | 5 | Auditor - Admin Capability | https://trello.com/c/SygUZ4rQ | - As an [Auditor], I want to [View logs for all courses] so that [I can report the overall usage to the State or University] - Acceptance Criteria: Auditors are able to view logs for current and previous course details | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10/6/2025 12:32:50 PM | Jacob Robidas | 11/19/2025 11:17:02 AM |  | 11/19/2025 10:56:44 AM | Eanes, Ronan | P43DT23H23M54S |  | Must | TRUE
| Scrum Board Test | Completed in Sprint 4 | 3 | Student - Messaging Capability | https://trello.com/c/fuW4YLE1 | - As a [Student], I want to [message other students and my instructor], so that [I can properly communicate with peers and instructor]. - Acceptance Criteria: Students may message each other and instructor from within the application. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10/6/2025 12:30:05 PM | Jacob Robidas | 11/19/2025 11:17:06 AM |  | 11/19/2025 10:56:13 AM | Eanes, Ronan | P43DT23H26M7S | Quinn Daniels | Should | TRUE
| Scrum Board Test | Completed in Sprint 4 | 32 | _Create Instructor View | https://trello.com/c/78q3N5mH | Create a proper View for the Instructors. There should be a way to see all the Courses they teach and the Students within. Potentially add another page where the Instructors who are admins can create a Course and assign Students to Courses. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 11/5/2025 12:20:26 PM | Jacob Robidas | 11/19/2025 11:17:08 AM |  | 11/19/2025 10:55:42 AM | Jacob Robidas | P13DT22H35M15S | Jacob Robidas,McKinney, Kaleb John | Must | TRUE
| Scrum Board Test | Completed in Sprint 4 | 1 | Instructor - student monitoring | https://trello.com/c/b4COI5QK | As an [Instructor], I want to [monitor my students’ activity through logs of timecards], so that [I can ensure they are working on assignments properly]. Acceptance Criteria: Instructors can view each student’s logged timecards. | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10/6/2025 12:25:48 PM | Quinn Daniels | 11/19/2025 11:17:12 AM |  | 11/19/2025 10:56:01 AM | Jacob Robidas | P43DT23H30M13S | McKinney, Kaleb John,Jacob Robidas | Must | TRUE
| Scrum Board Test | Completed in Sprint 4 | 24 | _Create an ERD | https://trello.com/c/Df6c4ps0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10/22/2025 11:58:13 AM | Jacob Robidas | 11/19/2025 11:17:14 AM |  | 11/19/2025 10:56:30 AM | Eanes, Ronan | P27DT23H58M16S | Jacob Robidas |  | TRUE

## Archived
Organization | Board | List | Card # | Title | Link | Description | Total Checklist items | Completed Checklist items | Checklists | NumberOfComments | Comments | Attachments | Votes | Spent | Estimate | Points Estimate | Points Consumed | Created | CreatedBy | LastActivity | Due | Done | DoneBy | DoneTime | Members | Labels | Due Complete | Start
| Scrum Board Test | Backlog / Cancelled Features | 18 | [archived] _JS Message System | https://trello.com/c/OddQFGDy |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10/20/2025 11:52:01 AM | Jacob Robidas | 11/19/2025 10:47:35 AM | [6 empty] | FALSE
| Scrum Board Test | Backlog / Cancelled Features | 21 | [archived] _Assess Unary Relationship for Students (Messaging) | https://trello.com/c/MpSxNYGj |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10/20/2025 11:56:28 AM | Jacob Robidas | 11/19/2025 10:47:38 AM | [6 empty] | FALSE